|  |
| --- |
|  |
| Release and Sprint Plans |
|  |
|  |
| **Sean and Jarad Little** |
| **28/11/2015** |

|  |
| --- |
|  |

Contents

[**Release 1** 3](#_Toc436511897)

[**Release 2** 3](#_Toc436511900)

[**Delivery Schedule** 4](#_Toc436511903)

[**Sprint 1** 4](#_Toc436511905)

[Story ID: 01 Home page 4](#_Toc436511906)

[Story ID: 03 Contact Info 4](#_Toc436511907)

[Story ID: 04 Trek Details 4](#_Toc436511908)

[Story ID: 11 Trek Cost Details 5](#_Toc436511909)

[**Sprint 2** 5](#_Toc436511910)

[Story ID: 02 Mission Statement and History of K.A.T 5](#_Toc436511911)

[Story ID: 09 Booking Form 5](#_Toc436511912)

[Story ID: 05 Medical, Visa, and Insurance Requirements 6](#_Toc436511913)

[Story ID: 07 Guide's Tips 6](#_Toc436511914)

[Release two 6](#_Toc436511915)

[**Sprint 3** 6](#_Toc436511916)

[Story ID: 06 Trail Map 6](#_Toc436511917)

[Story ID: 08 Fitness Advice from Guides 6](#_Toc436511918)

[Story ID: 10 Trek Itinerary 7](#_Toc436511919)

[Story ID: 12 Sitemap 7](#_Toc436511920)

**Release Plan**

**Release 1**

Delivery date: Total Story Points: 110

This release outlines the core components and features of the website. It focuses on the user’s experience by the design and implementation of the ability to book and view the most important information.

**Home Page and Basic Add ons**

This feature allows prospective tenants to search and view properties within the website. The owner of the website can host the properties for rent.

|  |  |  |
| --- | --- | --- |
| **Story ID** | **Story Title** | **Story Points** |
| **1** | Home page | 32 |
| **3** | Contact Info (About Us page) | 2 |
| **4** | Trek Details | 16 |
| **11** | Trek Cost Details | 4 |
|  | Story Point Sub-Total: | 54 |
|  |  |  |

**Booking form and Important Information**

This feature allows users to book using a form that will supply the company with the necessary information. It will also allow users to gain access to the necessary information that they will need before they come on their trip.

|  |  |  |
| --- | --- | --- |
| **Story ID** | **Story Title** | **Story Points** |
| **2** | Mission Statement and History (About us) | 8 |
| **9** | Booking Form | 32 |
| **5** | Medical, Visa, and Insurance Requirements | 8 |
| **7** | Guide's Tips | 8 |
|  | Story Point Sub-Total: | 56 |

**Release 2**

Delivery date: Total Story Points: 48

This release will focus on delivering additional content that gives additional value to the site, and additional information such as a map, advice, and itinerary's.

**Additional Information**

This feature will provide the site with more content to create credibility for the site.

|  |  |  |
| --- | --- | --- |
| **Story ID** | **Story Title** | **Story Points** |
| **6** | Trail Map | 32 |
| **8** | Fitness Advice | 4 |
| **10** | Trek Itinerary's | 4 |
| **12** | Sitemap | 8 |
|  | Story Point Sub-Total: | 48 |

**Delivery Schedule**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Week 1  Dec. 06 | Week 2  Dec. 13 | Week 3  Jan. 03 | Week 4  Jan. 10 | Week 5  Jan. 17 | Week 6  Jan. 24 |
| Sprint 1 | | Sprint 2 | | Sprint 3 | |
| Release 1 Jan. 16 | | | | Release 2 Jan. 30 | |

Estimated Velocity: 10.5

**Sprint Plan**

**Sprint 1**

Total Story Points: 54 points   
Total Hours: 5.5 hr

Current Velocity: 10

## Story ID: 01 Home page

|  |  |  |  |
| --- | --- | --- | --- |
| **Task ID** | **Task Description** | **Estimate** | **Taken** |
| 1 | Create the header and navigation bar. Style with CSS. | .5 hr |  |
| 2 | Seal in wrapper and style background image and translucent content/footer section. | .5 hr |  |
| 3 | Add content for body and footer. | .25 hr |  |
| 4 | Testing | N/A |  |
|  | Story Points: 32 Total Hours: | 1.25 hrs |  |

## Story ID: 03 Contact Info

|  |  |  |  |
| --- | --- | --- | --- |
| **Task ID** | **Task Description** | **Estimate** | **Taken** |
| 1 | Create About Us page from template | 0 hr |  |
| 2 | Add contact info to body and style with CSS | .5 hr |  |
| 3 | Testing | N/A |  |
|  | Story Points: 2 Total Hours: | .5 hr |  |

## Story ID: 04 Trek Details

|  |  |  |  |
| --- | --- | --- | --- |
| **Task ID** | **Task Description** | **Estimate** | **Taken** |
| 1 | Create Trek Info page from template | 0 hr |  |
| 2 | Generate info each trek and style with CSS | 1 hr |  |
| 3 | Add images for each trek | .75 hr |  |
| 4 | Testing | N/A |  |
|  | Story Points: 16 Total Hours: | 1.75 hrs |  |

## Story ID: 11 Trek Cost Details

|  |  |  |  |
| --- | --- | --- | --- |
| **Task ID** | **Task Description** | **Estimate** | **Taken** |
| 1 | Create Cost Details page from template | .5 hr |  |
| 2 | Generate information in table format and style with CSS | 1.5 hr |  |
| 3 | Testing | N/A |  |
|  | Story Points: 4 Total Hours: | 2 hrs |  |

**Sprint 2**

Total Story Points: 56 points   
Total Hours: 6.5 hr

Current Velocity: 9

## Story ID: 02 Mission Statement and History of K.A.T

|  |  |  |  |
| --- | --- | --- | --- |
| **Task ID** | **Task Description** | **Estimate** | **Taken** |
| 1 | Add statement and history to About Us and anchor at different levels on the page. | .75 hr |  |
| 2 | Style the content with CSS | .5 hr |  |
| 3 | Testing | N/A |  |
|  | Story Points: 32 Total Hours: | 1.25 hrs |  |

## Story ID: 09 Booking Form

|  |  |  |  |
| --- | --- | --- | --- |
| **Task ID** | **Task Description** | **Estimate** | **Taken** |
| 1 | Create Trek Booking page from template | 0 hr |  |
| 2 | Create form with HTML and CSS | .5 hr |  |
| 3 | Use javascript to Validate empty fields | .75 hr |  |
| 4 | Use php to validate incorrectly formatted values (including security threats) | 1.5 hr |  |
| 5 | Use php to send the content to the companies email addresses on successful submission | .75 |  |
| 6 | Testing | N/A |  |
|  | Story Points: 2 Total Hours: | 3.5 hr |  |

## Story ID: 05 Medical, Visa, and Insurance Requirements

|  |  |  |  |
| --- | --- | --- | --- |
| **Task ID** | **Task Description** | **Estimate** | **Taken** |
| 1 | Create Kokoda Information page from template | 0 hr |  |
| 2 | Add content to body and style with CSS | .5 hr |  |
| 3 | Add necessary links to sites that assist with obtaining relevant requirements | .5 hr |  |
| 4 | Testing | N/A |  |
|  | Story Points: 16 Total Hours: | 1 hr |  |

## Story ID: 07 Guide's Tips

|  |  |  |  |
| --- | --- | --- | --- |
| **Task ID** | **Task Description** | **Estimate** | **Taken** |
| 1 | Add section to Kokoda Information page | 0 hr |  |
| 2 | Generate tips in table format and style with CSS | .75 hr |  |
| 3 | Testing | N/A |  |
|  | Story Points: 4 Total Hours: | .75 hrs |  |

## Release two

**Sprint 3**

Total Story Points: 48 points   
Total Hours: 4.25 hr

Current Velocity: 12

## Story ID: 06 Trail Map

|  |  |  |  |
| --- | --- | --- | --- |
| **Task ID** | **Task Description** | **Estimate** | **Taken** |
| 1 | Use Google maps to generate a map of the trail | .75 hr |  |
| 2 | Use CSS to format the map into the page in an appealing way | .75 hr |  |
| 3 | Testing | N/A |  |
|  | Story Points: 32 Total Hours: | 1.5 hrs |  |

## Story ID: 08 Fitness Advice from Guides

|  |  |  |  |
| --- | --- | --- | --- |
| **Task ID** | **Task Description** | **Estimate** | **Taken** |
| 1 | Add section to the Kokoda Information page | 0 hr |  |
| 2 | Create a short paragraph detailing how challenging the trek is, and how fit one must be to walk it. | .5 hr |  |
| 3 | Testing | N/A |  |
|  | Story Points: 2 Total Hours: | .5 hr |  |

## Story ID: 10 Trek Itinerary

|  |  |  |  |
| --- | --- | --- | --- |
| **Task ID** | **Task Description** | **Estimate** | **Taken** |
| 1 | Create Trek Itinerary page from template and add the link to the Trek Information page | 0 hr |  |
| 2 | Add content (from supplied info pages) to the pages with subheadings of days | 1 hr |  |
| 3 | Style with CSS | .5 hr |  |
| 4 | Testing | N/A |  |
|  | Story Points: 16 Total Hours: | 1.5 hr |  |

## Story ID: 12 Sitemap

|  |  |  |  |
| --- | --- | --- | --- |
| **Task ID** | **Task Description** | **Estimate** | **Taken** |
| 1 | Create sitemap page from template | 0 hr |  |
| 2 | Generate links to each page in the site and style with CSS | .75 hr |  |
| 3 | Testing | N/A |  |
|  | Story Points: 4 Total Hours: | .75 hrs |  |